## Slide 1: GitLab Migration
Objective: Streamline CI/CD workflows by migrating from Jenkins to GitLab.
Timeline: October 2024 to December 2026

## Slide 2: EMM Digital | Overall GitLab Migration Plan
Chart: EMM Digital | Overall GitLab Migration
| Planning Phase | Environment Set up | Pipeline Migration | Testing and Validation | Go-Live
Start Date | 45566 | 45627 | 45627 | 45717 | 46082
Duration | 150 | 89 | 365 | 364 | 92
Notes: Planning Phase: Completed (e.g., requirements gathering, risk analysis).
Environment Setup: Completed (e.g., GitLab instance set up and configured).
Pipeline Migration: In Progress (e.g., Jenkins jobs converted to GitLab pipelines).
Testing and Validation: Upcoming (e.g., pipeline testing and bug fixes).
Go-Live: Future (e.g., full switch to GitLab).

## Slide 3: GitLab Migration Plan | Progress so far
Chart: 
| Completed | Upcoming
Sales | 0.14 | 0.86
Progress Summary
Total Pipelines Migrated: 14 out of 140.
Teams Onboarded: 2 out of 10.
Dependencies Resolved: 2 out of 10.
Chart: Migration Plan Overview Oct2024 – March 2025
| Move to GitLab | ORAC Completion | Cutover/Go-Live
Start Date | 45627 | 45688 | 45716
Duration | 61 | 28 | 31
Task | 0 | 0 | 0
10% Migration Plan overview by Q1 2025
Repositories migrated since Oct 2024

## Slide 4: Migration Plan | Achievements and Challenges
Achievements So Far
Cloned 14 repositories from Stash to Gitlab (10% Migration)
Created CI pipeline for all 14 repositories
Current Challenges
Veracode SCA token generation.
Pipelines to be created for UI.

## Slide 5: Migration Plan | Next Steps
Complete 10% Gitlab migration by Q1 2025.
Complete the ORAC requirements for the 10% migration by Q1 2025
Cutover from Stash + Jenkins to Gitlab for Developers by Q2 2025
Conduct training sessions for teams.
Monitor and optimize performance post-migration.

## Slide 6
Chart: 
| Planning Phase | Enviornment Set up | Pipeline Migration | Testing and Validation | Go-Live
Completed | 4.3 | 2.5 | 3.5 | 4.5 | 4.5
In Progress | 2.4 | 4.4 | 1.8 | 2.8 | 5
Upcoming | 2 | 2 | 3 | 5 | 6

## Slide 7
Chart: Migration Progress
| Move to GitLab | ORAC Completion | Cutover/Go-Live
Start Date | 45566 | 45688 | 45716
Duration | 122 | 28 | 31
Task | 0 | 0 | 0